# Why Software Estimates Are Wrong

What 80,709 tasks from three independent sources say about what is predictable in estimation error — and what is not

Data: Derek Jones — Software estimation datasets Code: `src/analysis.py` · Notebook: `notebooks/`

# Executive summary

The central question: can we predict that a task will be underestimated, and what factors explain the estimation error?

The short answer: what is predictable is not the task but the circumstances. A model given only the developer's estimate predicts underestimation at coin-flip level (ROC-AUC 0.49). Add context — who, which project, which phase — and AUC rises to 0.71. The estimate carries no information about its own error.

Of seven testable hypotheses, three were refuted, including the two most popular ones.

| RQ | hypothesis | verdict |
| --- | --- | --- |
| RQ1 | Developers systematically underestimate | refuted — the aggregate shows overestimation |
| RQ2 | Larger tasks are underestimated more | refuted, opposite sign |
| RQ3 | Accuracy depends on the person | supported in CESAW (R² 0.10), not in SiP (0.03) |
| RQ4 | Project explains part of the variation | supported, small effect (0.03) |
| RQ5 | Type of work matters | supported, small effect (0.04) |
| RQ6 | Interruptions relate to the error | supported, the strongest factor found |
| RQ7 | Round-number estimates are less accurate | not supported — a confounder |

# 1. Data and method

| dataset | tasks | units | period | role |
| --- | --- | --- | --- | --- |
| CESAW | 60,284 | minutes | 2008–2017 | primary: 247 people, 45 projects, has interruptions |
| SiP | 10,266 | hours | 2004–2014 | validation on a different organisation |
| Renzo Pomodoro | 10,159 | pomodoros | 2009–2019 | validation on a single person |

CESAW is the primary set: enough data for non-toy ML and, unlike PROMISE/COCOMO where a row is a whole project, it carries an estimate → actual pair for an individual task.

Everything is computed in log space. actual/estimate is a strictly positive, skewed quantity (maximum ×298). In logs, "twice as long" and "half as long" are symmetric, the mean of log_ratio is the log of the geometric mean, and exp(MAE_log) reads as "typically wrong by a factor of N".

## What one row means — and why this took longer than the ML

The CESAW description advertises "203,621 observations". Those are not tasks: the archive holds two tables — 61,817 tasks and 203,621 work sessions (timer entries). The link between them is undocumented. The key was recovered by search:

| key tested | groups out of 61,817 rows |
| --- | --- |
| (project, wbs, plan_item) | 51,582 — not unique |
| + phase | 51,582 — not unique |
| + phase, person | 61,817 — unique ✔ |

Confirmation rather than coincidence: aggregating sessions by that key reproduces task_actual_time_minutes for 99.3% of tasks.

A similar trap exists in SiP: 12,299 rows but 10,266 tasks — multi-person tasks are stored as several rows with duplicated estimate and actual. Without deduplication, large tasks get 2–5× the weight.

The full log of cleaning decisions is in results/01_cleaning_log.csv.

# 2. The trap that must be removed before any modelling

In 8% of CESAW tasks, 34% of SiP and 44% of Renzo, the actual equals the estimate exactly.

The exact-match artefact

These are not perfect estimates. The share of exact matches falls from about 60% on half-hour tasks to about 1% on multi-day ones: logging time "as planned" is easy on a short task and impossible on a long one. This is a logging practice.

Why it is critical: the "actual = estimate" baseline gets zero error on those rows for free, which makes it nearly unbeatable on median metrics. Every key result is therefore computed twice — on all data and on the subset with exact matches removed.

This is also why CESAW (8%) is a more honest basis than SiP (34%).

# 3. RQ1–RQ2: there is no systematic underestimation, there is regression to the mean

## RQ1 — hypothesis refuted

|  | CESAW | SiP | Renzo |
| --- | --- | --- | --- |
| N | 55,393 | 6,767 | 5,703 |
| share underestimated | 42.4% | 45.6% | 49.1% |
| geometric mean actual/estimate | 0.799 | 0.860 | 0.947 |
| p (log_ratio vs 0) | < 1e−300 | 4e−32 | 8e−7 |

In all three sources the bias runs toward overestimation. The folklore "multiply by two" is wrong not in magnitude but in sign.

A curious detail on Renzo: the sign test does not reject 50% (p = 0.20) while the t-test on log_ratio does (p = 8e−7). There is no contradiction — tasks exceed their estimate about half the time, but the overruns are smaller in magnitude than the underruns. The person is calibrated in frequency but not in magnitude.

## RQ2 — hypothesis refuted, opposite sign

The size effect

| size | CESAW | SiP |
| --- | --- | --- |
| ≤ 0.5 h | ×0.98 | ×1.30 |
| 0.5–1 h | ×0.76 | ×1.18 |
| 1–2 h | ×0.70 | ×1.10 |
| 2–4 h | ×0.68 | ×0.97 |
| 4–8 h | ×0.67 | ×0.82 |
| 8–16 h | ×0.67 | ×0.75 |
| > 16 h | ×0.57 | ×0.51 |

The slope of log_ratio ~ log_est is negative everywhere: CESAW −0.169, SiP −0.240, Renzo −0.805, all p < 1e−140. The mechanism is regression to the mean: the estimate is a noisy signal, and extreme estimates in either direction are pulled toward a typical task duration.

In SiP the bias literally changes sign (×1.30 → ×0.51). In CESAW the sign does not change, but the trend is the same. For the single person (Renzo) the slope is three to five times steeper: without organisational averaging, the effect shows most clearly.

Replication

Practical conclusion: a single "safety coefficient" for a team is harmful — it errs in opposite directions on different tasks. Calibrate by size: multiply small, divide large.

# 4. RQ3–RQ5: significant ≠ important, and the dominant factor depends on the organisation

Naive R² is deceptive: person has 246 levels in CESAW, i.e. 246 dummy variables. So we also compute an adjusted and an out-of-sample R² (5-fold CV) — the last one cannot be inflated by level count.

| factor | CESAW: R² | R² adjusted | R² out-of-sample | SiP: R² out-of-sample |
| --- | --- | --- | --- | --- |
| person | 0.112 | 0.108 | 0.103 | 0.026 |
| phase / type of work | 0.044 | 0.042 | 0.040 | 0.023 |
| project | 0.032 | 0.031 | 0.030 | 0.012 |
| task size | 0.021 | 0.021 | 0.021 | 0.080 |
| all factors combined | 0.182 | 0.176 | 0.170 | 0.137 |

Bias by factor

Two conclusions.

The dominant factor differs between organisations. In CESAW the person matters most (10% of variance; the effect survives both the adjustment and cross-validation, so it is real). In SiP it is the reverse: the person contributes almost nothing while task size explains 8%. "What matters here is who estimates" cannot be carried between companies — it is a property of the organisation, not of software development.

The ceiling is low. All observed factors combined explain 17% of the variance in CESAW and 14% in SiP. That is, 83–86% of the variance in estimation error is explained by nothing recorded in the data. Section 7 follows directly from this: a point prediction is doomed, and the right product is an interval.

# 5. RQ6: work fragmentation is the strongest factor found

Interruptions

| task size | uninterrupted | interrupted |
| --- | --- | --- |
| ≤ 0.5 h | ×0.92 | ×2.01 |
| 0.5–1 h | ×0.68 | ×1.50 |
| 1–2 h | ×0.59 | ×1.25 |
| 2–4 h | ×0.53 | ×1.11 |
| 4–8 h | ×0.50 | ×1.00 |
| 8–16 h | ×0.47 | ×0.96 |
| > 16 h | ×0.37 | ×0.75 |

The effect holds within every size band and is larger than anything RQ3–RQ5 produced: interrupted tasks overrun roughly twice as much. The same pattern appears across session counts — from ×0.59 at one session to ×2.37 above sixteen.

But the conclusions are doubly limited. Causal direction is not established: interruptions may lengthen a task, or they may be a consequence of a task turning out harder and stretching over many days. And for prediction it is useless: at estimation time the interruptions have not happened, so they were excluded from the model's features.

# 6. RQ7: how a good-looking hypothesis falls apart

The original CESAW work flags a tendency toward round numbers as an accuracy factor. The raw comparison agrees: round estimates give ×0.77, non-round ×0.83.

Round numbers

But the median round estimate is 1 hour while the median non-round one is 0.72 hours. Round estimates are simply used more often on larger tasks, and larger tasks are overestimated per RQ2. Comparing within size bands, the direction stops being consistent: in some bands round estimates are more accurate, in others worse.

The observed effect is explained by task size, not by roundness. The confounder here is size, and it correlates with almost everything in this data.

# 7. Machine learning

## 7.1 The split strategy shifts conclusions more than the choice of model

The data contains repeated observations of the same people and projects. A random split lets the model see the same person on the same project in both train and test.

| strategy | what it tests | RMSE gain | ROC-AUC | PR-AUC |
| --- | --- | --- | --- | --- |
| A. Random | basic learnability | 18.5% | 0.775 | 0.688 |
| B. Unseen projects | transfer to a new project | 12.7% | 0.738 | 0.648 |
| C. Temporal | predicting the future from the past | 10.2% | 0.709 | 0.556 |

Reporting the random split would have inflated everything. Everything below uses C — the only strategy matching the real scenario.

## 7.2 Regression: predicting the size of the error

We predict log_ratio (a correction to the estimate) rather than log(actual), so the developer's estimate stays in the prediction as an anchor.

| model | MAE_log | typical error | RMSE_log | MdMRE | PRED(25) |
| --- | --- | --- | --- | --- | --- |
| constant | 1.242 | ×3.46 | 1.569 | 0.808 | 0.133 |
| B0: actual = estimate | 0.694 | ×2.00 | 1.053 | 0.408 | 0.390 |
| B1: global ×0.80 | 0.729 | ×2.07 | 1.041 | 0.405 | 0.383 |
| B2: log-linear calibration | 0.750 | ×2.12 | 1.045 | 0.452 | 0.297 |
| M1: Ridge + features | 0.739 | ×2.09 | 1.003 | 0.547 | 0.249 |
| M2: Gradient Boosting | 0.673 | ×1.96 | 0.946 | 0.429 | 0.331 |

## 7.3 Classification: predicting the fact of underestimation

The base rate on the test set is 35.7%, so accuracy is uninformative; PR-AUC is the measure to watch.

| model | accuracy | precision | recall | F1 | ROC-AUC | PR-AUC |
| --- | --- | --- | --- | --- | --- | --- |
| Baseline: class share | 0.643 | 0.000 | 0.000 | 0.000 | 0.500 | 0.357 |
| Logistic regression | 0.680 | 0.596 | 0.328 | 0.423 | 0.693 | 0.548 |
| Decision tree (depth=6) | 0.670 | 0.560 | 0.359 | 0.438 | 0.663 | 0.503 |
| Random Forest | 0.696 | 0.692 | 0.268 | 0.386 | 0.735 | 0.595 |
| Gradient Boosting | 0.680 | 0.596 | 0.324 | 0.419 | 0.709 | 0.556 |

Classification

Random Forest beat boosting on both ROC-AUC and PR-AUC — added model complexity does not always pay. Recall is low (0.27): at a 0.5 threshold the model catches only a quarter of the underestimated tasks, but with 0.69 precision. The threshold is of course tunable to the cost of each error.

## 7.4 The key experiment: where the predictive power comes from

Ablation

| feature set | MAE_log | RMSE_log | ROC-AUC | PR-AUC |
| --- | --- | --- | --- | --- |
| estimate only | 0.766 | 1.055 | 0.492 | 0.348 |
| + context (project / phase / person) | 0.689 | 0.963 | 0.692 | 0.539 |
| + history (leak-free) | 0.673 | 0.946 | 0.709 | 0.556 |

(B0 "actual = estimate": MAE_log 0.694, RMSE_log 1.053)

This is the key result of the project. A model that knows only the estimate predicts underestimation at ROC-AUC 0.49 — no better than a coin flip — and on MAE it is worse than simply trusting the estimate.

In other words: the estimate contains no information about whether it is wrong. A developer does not "somewhat know" about their error — they know nothing about it.

All the predictive power arrives with context. The answer to RQ8: underestimation can be predicted, but not from the estimate — from the circumstances.

## 7.5 Leak-free historical features

The most valuable feature is "how wrong was this person before". A naive groupby(person).log_ratio.mean() would use the future. The correct construction is an expanding mean shifted by one step in chronological order. The absence of leakage is checked automatically: the first task of every person must have NaN history.

The contribution is modest (AUC 0.692 → 0.709), and tellingly, recent accuracy (person_recent_lr, a rolling window of 10 tasks) works noticeably better than accuracy accumulated over all time: estimator behaviour drifts.

# 8. Explainability

SHAP

Permutation importance and SHAP agree: log_est, person, person_recent_lr and phase_short_name dominate. is_round contributes nothing — independent confirmation of the RQ7 verdict. person_hist_lr (accumulated history) loses to person_recent_lr (recent history) — further evidence of drift.

## Where the model fails

| task size | N | B0 MAE_log | GBM MAE_log | gain |
| --- | --- | --- | --- | --- |
| ≤ 0.5 h | 5,618 | 0.660 | 0.642 | +2.7% |
| 0.5–1 h | 3,341 | 0.706 | 0.679 | +3.8% |
| 1–2 h | 2,558 | 0.761 | 0.719 | +5.5% |
| 2–4 h | 1,676 | 0.783 | 0.732 | +6.6% |
| 4–8 h | 1,064 | 0.677 | 0.671 | +0.9% |
| 8–16 h | 644 | 0.538 | 0.600 | −11.6% |
| > 16 h | 170 | 0.442 | 0.604 | −36.6% |

Error analysis

On large tasks the model loses to the baseline, and by a wide margin. The N column shows why: large tasks are rare and their spread is widest. The model pulls predictions toward typical behaviour and systematically undershoots them (mean bias −0.24).

Practical conclusion: apply the model only to small and medium tasks and keep the developer's estimate on large ones. The headline "10% gain" without this breakdown would be misleading.

# 9. What can actually be handed to a team

## Personal calibration works halfway

| model | MAE_log | RMSE_log |
| --- | --- | --- |
| B0: actual = estimate | 0.694 | 1.053 |
| personal coefficient (≥5 past tasks) | 0.716 | 0.997 |
| personal coefficient (≥20 past tasks) | 0.716 | 0.999 |
| global coefficient ×0.80 | 0.729 | 1.041 |
| Gradient Boosting | 0.673 | 0.946 |

The personal coefficient improves RMSE but worsens MAE: it helps on outliers and hurts on typical tasks. The history threshold changes nothing — the issue is not data volume but that personal bias explains too little (RQ3).

## An interval instead of a number

If 83–86% of the variance is irreducible, a point prediction is meaningless. We build quantile regression (10% and 90% quantiles of log_ratio) and calibrate it with conformalized quantile regression.

Intervals

|  | coverage | median width |
| --- | --- | --- |
| raw quantile regression | 73.2% | ×6.1 |
| after CQR calibration | 78.3% | ×8.0 |

The nominal target is 80%. Calibration lifts coverage from 73% to 78% but does not reach nominal: exchangeability is broken by the non-stationarity of the process. Claiming exactly 80% would be untrue.

What a developer's estimate actually means (80% range):

| estimate | lower bound | upper bound | observed coverage |
| --- | --- | --- | --- |
| ≤ 0.5 h | ×0.35 | ×3.0 | 0.79 |
| 0.5–1 h | ×0.30 | ×2.4 | 0.75 |
| 1–2 h | ×0.29 | ×2.15 | 0.75 |
| 2–4 h | ×0.26 | ×1.98 | 0.74 |
| 4–8 h | ×0.26 | ×2.06 | 0.72 |
| 8–16 h | ×0.32 | ×1.71 | 0.69 |

The intervals are wide — that is not a defect of the model but a measured property of the domain.

# 10. Conclusions

About estimates:

- Check what you are measuring first. The share of exact matches by task size is a free health test for the data. If it falls from 60% to 1%, you are measuring logging discipline, not estimation accuracy.

- There is no systematic underestimation — there is regression to the mean. It replicates across three independent sources with different industries and units.

- The dominant factor depends on the organisation (person in CESAW, task size in SiP), but the ceiling is low everywhere: 83–86% of the variance is explained by nothing.

- Work fragmentation is the strongest factor found (×2 within every size band), but causality is not established and it is unavailable for prediction.

- The round-number effect did not hold up — it is an artefact of task size.

About predictability:

- The estimate contains no information about its own error (ROC-AUC 0.49). The circumstances are predictable; the task is not.

- The split strategy shifts conclusions more than the choice of model.

- ML wins on small and medium tasks and loses on large ones.

- Personal coefficients work halfway.

- Hand over an interval — and say honestly that it falls short of nominal.

What a team should do:

- Check your logging before building any accuracy dashboards.

- Drop the single safety coefficient; calibrate by task size.

- Measure what dominates in your own organisation — it is one R² table, and it decides where effort is worth spending.

- Protect focus: fragmentation is the only strong controllable factor found.

- Plan with intervals. A "4 hours" estimate here means an 80% range of roughly one to eight hours.

# 11. Limitations

- Observational data. We do not know whether the estimate influenced the actual: a developer may have paced the work to the quoted deadline (self-fulfilling prophecy). Inseparable without an experiment.

- Survivorship bias. Unfinished and cancelled tasks are absent from the datasets; the conclusions are likely biased optimistic.

- RQ6 is not causal. The association between interruptions and overrun is established; the direction is not.

- Exchangeability for CQR is broken, so coverage was checked empirically on each window (0.76–0.81) and falls short of the nominal 80%.

- CESAW is a specific environment (formal TSP process, some safety-critical projects). SiP and Renzo confirm the direction of the effects but not their magnitude.

- The model is unfit for large tasks — see section 8.

# 12. Next steps

- A hierarchical Bayesian model: partial pooling across person and phase would give stable estimates for rare categories instead of noisy group means — and would probably fix the failure on large tasks.

- A censored-observation model for unfinished tasks, to remove the survivorship bias.

- Aggregation to sprint level: do individual task errors cancel out or compound? For planning this is the central question, and the CESAW data can answer it.

- The WBS hierarchy (wbs_parent.csv) remains unused.

# Reproducing this

``bash pip install -r requirements.txt python src/analysis.py        # ~2 minutes, writes reports/figures/ and results/ ``

Or open the notebook in Google Colab — the data downloads automatically.